## Sheet1
LEGEND: |  |  |  | CALENDAR: | 1/25-1/29 | 2/1-2/5 | 2/8-2/12 | 2/15-2/19 | 2/22-2/26 | 3/1-3/5 | 3/8-3/12 | 3/15-3/19 | 3/22-3/26 | 3/29-4/2 | 4/5-4/9 | 4/12-4/16 | 4/19-4/23 | 4/26-4/30
| complete/ low risk | pending/ medium risk | not started/ high risk
| Deadline | Start | Status | Complete? | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Risk/Challenges | Mitigation
AML Process Phase 3
Understand Current AML Process and Bottlenecks | 2021-02-06 | 2021-01-25 | Done | 100% | bar: Week 1 to Week 2
Receive and Confirm the First Quarter Contracts List | 2021-02-08 | 2021-02-08 | Done | 100% | bar: Week 3
Create and Automate Project Tracker and Visualizations for 2021 Contracts | 2021-02-16 | 2021-02-08 | Done | 100% | [16 empty] | Utilizing VBA Code and Macros for Checkboxes and Tracker Features | Manually Link Checkboxes with Data Cells to Mitigate the Risk of Running into Macro-Enabled Issues | bar: Week 3 to Week 4
First Quarter Contract Automation | 2021-02-20 | 2021-02-16 | Done | 100% | [16 empty] | Gaining Access to Finalized AML Vendor List in Excel Format | Communication with Anne Wilson | bar: Week 3 to Week 4
Present Contracts Tracker First 2 Drafts and Implement Feedback | 2021-02-22 | 2021-02-09 | Done | 100% | bar: Week 4 to Week 6
Analyze 2021 New Vendor List | 2021-03-22 | 2021-02-08 | Done | 100% | bar: Week 4 to Week 6
AML Phase 3 Business Process Walkthrough with IT Team | 2021-02-23 | 2021-02-23 | Done | 100% | bar: Week 5 to Week 6
Create/Merge AML Database to One Combined IT Contract List | 2021-02-23 | 2021-02-23 | Done | 100% | bar: Week 5
Add In Additional Features Requested on Compiled Project Tracker | 2021-03-01 | 2021-02-23 | Done | 100% | bar: Week 5
Finalize and Present AML Contract Tracker Final Version | 2021-03-02 | 2021-02-18 | Done | 100% | bar: Week 6
Input and Check Accuracy of Dates in AML Application | 2021-03-08 | 2021-03-03 | Done | 100% | bar: Week 6 to Week 7
Report the Updated and Pending Contracts with Legend and Comments | 2021-03-17 | 2021-03-04 | Done | 100% | [16 empty] | Lack of Ability to Access Procurement Folders to Update Contracts | Notified Justyna- in progress | bar: Week 7 to Week 8
Comparison Analysis: Tracker vs Application | 2021-03-26 | 2021-03-14 | Done | 100% | bar: Week 8
AML Application Contracts Content Additions and Update | 2021-03-29 | 2021-03-24 | Done | 100% | [16 empty] | Disparity of Information between Platforms | Created Specialized Reports for Mgmt | bar: Week 9
Create Guidebook for Project Tracker | 2021-03-29 | 2021-03-15 | Done | 100% | bar: Week 8 to Week 9
AML Invoice Attachments - Application | 2021-04-05 | 2021-03-27 | Done | 100% | [16 empty] | Variety of Invoices and Files; Difficulty Identifying Correct Invoices | Working Progress; Consultation with IT | bar: Week 9 to Week 10
Analyze Data on Different Platforms and Integrate Contracts into 1 Database | 2021-04-05 | 2021-03-24 | Done | 100% | bar: Week 9 to Week 11
Prepare AML Finalized Spreadsheet for Automation Tasks | 2021-04-05 | 2021-03-26 | Done | 100% | bar: Week 10 to Week 11
Update Notification Recipient, Vendor, and DO Details on Final AML | 2021-04-14 | 2021-04-05 | Done | 100% | [16 empty] | Lacking Major DO Information to Finalize Spreadsheet | Working wtih Anne and Nadine to Get Information; Conclusion: 3 fields (Contract Term, DO Date and Total) will be Updated by Anne & Nadine overtime | bar: Week 12
Compose the Final Deliverable Documentations | 2021-04-24 | 2021-03-15 | Done | 100% | bar: Week 12 to Week 13
Automate Alerts for 90/60/30 Days to Contract Stakeholders | 2021-04-26 | 2021-04-10 | Pending | 0 | [16 empty] | Jason (IT Specialist) is Unavailable; Potential Time Pressure | Working on Figuring Out Alternatives and Working with Matt | bar: Week 13 to Week 14
Submit Final Report and Deliverables to Fulton County Drive | 2021-04-24 | 2021-04-01 | Done | 100% | bar: Week 14
| Deadline | Start | Status | Complete? | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Risk/Challenges | Mitigation
Analytics/Statistics/Visualization/Databasing |  |  | On Schedule
Find data in the database that could be use as important KPIs. | 2021-01-29 | 2021-01-25 | Started | 100% | bar: Week 1 to Week 2
Presentation of KPIs and visualization of the KPIs using Tableau | 2021-02-05 | 2021-02-01 | Started | 100% | bar: Week 2 to Week 3
Create a framework for the project | 2021-02-10 | 2021-02-08 | Started | 100% | bar: Week 3 to Week 4
Identify missing data in the database | 2021-02-19 | 2021-02-08 | Started | 100% | [16 empty] | Missing Data points in the Database | Searching for past Capstone project in the P Drive | bar: Week 4 to Week 5
Create a Survey to Collect Information | 2021-02-28 | 2021-02-22 | Started | 100% | bar: Week 5
Follow Up Phone Call Reminders to Complete the Survey | 2021-03-23 | 2021-03-01 | Started | 100% | [16 empty] | Incomplete Surveys, People being Unreachable(Voicemails, Hang Ups etc) | Contacting through Emails, Phone, and LinkedIn | bar: Week 6 to Week 8
Interview the Capstone Sponsors, Organize Collected Information | 2021-04-01 | 2021-03-09 | Started | 100% | [16 empty] | Schedualing problems for Interviews | Check for scheduale openings, emails meeting invites with agenda | bar: Week 7 to Week 8
Create Dashboards for the KPIs: Service, Impact and Efficiency | 2021-04-13 | 2021-03-23 | Started | 100% | bar: Week 8 to Week 10
Upload Dashboards to Tableau Sever | 2021-04-20 | 2021-04-14 | Not Started | 75%
Final Project Documentation and Deliverables | 2021-04-26 | 2021-04-21 | Started | 40%
| Deadline | Start | Status | Complete? | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Risk/Challenges | Mitigation
Court Automation
Understanding of the CA project evaluation and presentation | 2021-02-12 | 2021-02-01 | Done | 100% | bar: Week 1 to Week 2
Bussiness Undrestanding | 2021-02-17 | 2021-02-08 | In-progress | 100% | [16 empty] | Not all resources are available | Meeting with Case manager and getting software with correct virsion | bar: Week 2 to Week 3
Model exploration | 2021-02-22 | 2021-02-16 | Not Started | 100% | bar: Week 3 to Week 4
Data Undrestanding | 2021-03-01 | 2021-02-08 | Not Started | 100% | bar: Week 4 to Week 5
data preparation for XGBoost | 2021-03-08 | 2021-03-01 | Not Started | 100% | bar: Week 6
Research on Financial Data | 2021-03-29 | 2021-03-08 | In-progress | 100% | bar: Week 6 to Week 8; Week 11
Create Fake Dashboard | 2021-03-22 | 2021-03-16 | In-progress | 100% | bar: Week 8 to Week 9
Change Color on Dashboard | 2021-04-03 | 2021-03-22 | Not Started | 100% | bar: Week 9
SOP | 2021-04-03 | 2021-03-18 | In-progress | 95% | bar: Week 8 to Week 9
Update XGBoost Model | 2021-04-12 | 2021-02-22 | In-progress | 100% | bar: Week 5 to Week 6; Week 9 to Week 13
Case Discoveries | 2021-04-07 | 2021-02-08 | Not Started | 100% | bar: Week 3 to Week 11
| Deadline | Start | Status | Complete? | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Risk/Challenges | Mitigation
SOP (Standard Operating Procedures) for the Agenda Management Application - Legistar
Research application to understand purpose, use, and identify the stakeholders. | 2021-02-11 | 2021-02-01 | Done | 100% | bar: Week 1
Navigating the Files Module | 2021-02-18 | 2021-02-11 | Done | 100% | bar: Week 2
Drafting Legislative Files | 2021-02-25 | 2021-02-18 | Done | 100% | bar: Week 3
Running Reports from the Legislative Files Interface | 2021-03-04 | 2021-02-25 | Done | 100% | bar: Week 4
**Routing Legislative Files through the Approval Tracking Sequence **Fulton County Approval Track Sequences | 2021-03-11 | 2021-03-04 | Done | 100% | bar: Week 5
Searching for Legislative Files | 2021-03-18 | 2021-03-11 | Done | 100 | bar: Week 6
Research and explain how to create an agenda with the approved legislative files and detail how to format, edit, and publish your agenda. | 2021-03-25 | 2021-03-18 | Not Started | 0%
Navigating the Agendas Module | 2021-04-01 | 2021-03-25 | Done | 100 | bar: Week 7
Generating an Agenda | 2021-04-15 | 2021-04-01 | Not Started | 0%
**Adding Copying and Deleting Agenda Lines **Running and Printing Agenda Reports **Deleting an Agenda in Legistar | 2021-04-22 | 2021-04-15 | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Status | Complete? | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Risk/Challenges | Mitigation
Endpoint Protection Software
Scope & Plan | 2021-02-04 | 2021-02-01 | Done | 100% | [16 empty] | Do not comprehend the end deliverables | bar: Week 1
Define/Research EDR | 2021-02-04 | 2021-02-01 | Done | 100% | [16 empty] | Project plan still not complete | bar: Week 2
Research Cylance Optics | 2021-02-11 | 2021-02-08 | Done | 100% | [16 empty] | No access to Cylance-Optices webpage, so reasearch is done from an outside view perspective | bar: Week 3
Work existing alerts | 2021-02-18 | 2021-02-15 | Done | 100% | [16 empty] | Cylance-optics access is done in an unorthodox way, but works | zoom call dakota and use cylance on his computer. | bar: Week 4
Continue working existing alerts | 2021-02-25 | 2021-02-22 | Done | 100% | [16 empty] | Cylance-optics access is done in an unorthodox way, but works | bar: Week 5
Create ruleset for testing on lab machine(s) | 2021-03-04 | 2021-03-01 | Done | 100% | bar: Week 6 to Week 7
Write custom rules for lab/test ruleset | 2021-03-11 | 2021-03-08 | Done | 100% | bar: Week 7 to Week 8
Continue rule creation/testing on lab machines | 2021-03-18 | 2021-03-15 | Done | 100% | [16 empty] | We cannot create any new rules since they involve coding | used the rules cylance provided for us | bar: Week 8 to Week 12
Improve existing rules | 2021-04-16 | 2021-03-22 | Done | 100% | bar: Week 8 to Week 12
Work on Documentation due below | 2021-04-26 | 2021-03-29 | PENDING | 100% | bar: Week 13 to Week 14
Full documentation of the proposed/created rules/rulesets. Recommend security, describe the process . How did this process improve Fulton's abilty to secure fulton county employees. | 2021-04-27 | 2021-04-05 | PENDING | 100% | bar: Week 13 to Week 14
| Deadline | Start | Status | Complete? | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Risk/Challenges | Mitigation
Identity & Access Management Improvement
Project Plan FC | 2021-02-09 | 2021-01-30 | Done | 100% | bar: Week 1 to Week 3
Define Idaptive & how will it be used in FC? | 2021-02-16 | 2021-02-10 | Done | 100% | [16 empty] | Finding availability for the meetings | bar: Week 3 to Week 4
Review current policies in Idaptive and how to create policies. | 2021-02-23 | 2021-02-17 | Done | 100% | bar: Week 3; Week 5
Idenitify if we have self-service enabled, why or why not that would be a good option to enable. Recommendations | 2021-03-02 | 2021-02-24 | Done | 100% | bar: Week 3; Week 5
After reviewing current Idaptive polices deployed in the environment, what other policies do you recommend. | 2021-03-09 | 2021-03-03 | Done | 100% | bar: Week 3; Week 6 to Week 7
Document how to configure an application to single sign on and what are the benefits. | 2021-03-23 | 2021-03-10 | Done | 100% | [16 empty] | Cancelled meeting (Zoom issue) | Deliverables will have to be delivered together | bar: Week 3; Week 7 to Week 9
Document how to assign apps to users or roles | 2021-03-30 | 2021-03-24 | Done | 100% | [16 empty] | Network outage at Fulton County | Deliverables will have to be delivered together | bar: Week 3; Week 10
Document process and would you recommend this setting. | 2021-04-06 | 2021-03-31 | Done | 100% | bar: Week 3; Week 11 to Week 12
Mobile Devices and Authentication | 2021-04-13 | 2021-04-07 | Done | 100% | bar: Week 3; Week 12
What is FIDO2 authenticators, how to enable it and should we set it up. | 2021-04-20 | 2021-04-14 | Done | 100% | bar: Week 3; x Week 13
-Evaluation of Idaptive plan and the ability to implement. | 2021-04-27 | 2021-04-21 | Done | 100% | bar: Week 3; x Week 14
| Deadline | Start | Status | Complete? | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Risk/Challenges | Mitigation
Requisitions & Invoices
Unerstand the project scope/ Current process analysis | 2021-02-08 | 2021-02-08 | Complete | 100% | bar: D Week 3
To be analysis | 2021-02-09 | 2021-02-08 | Complete | 100% | bar: D Week 3
Project plan | 2021-02-09 | 2021-01-09 | Complete | 100% | bar: D Week 4
Gain knowledge of RemedyForce | 2021-02-18 | 2021-02-18 | Complete | 100% | bar: D Week 5
Condust research on Adobe and DocuSign | 2021-02-03 | 2021-02-22 | Complete | 100% | bar: D Week 6
Find a API between Adobe/ DocuSign and RemedyForce | 2021-03-08 | 2021-02-22 | Complete | 100% | bar: D Week 6
Create traceability matrix | 2021-03-22 | 2021-03-15 | Complete | 100% | bar: D Week 7 to D Week 8
Meeting with docusign admin |  |  | complete | 100% | bar: D Week 10
Schedule meeting with vendor to dicuss cost and implementation |  |  | Complete | 100% | bar: D Week 6 to D Week 11
document meeting with vendor |  |  | complete | 100% | bar: D Week 12
Make final decision on Adobe or docuSign |  |  | complete | 100% | bar: D Week 12
| Deadline | Start | Status | Complete? | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Risk/Challenges | Mitigation
Mapping & Alignment of Kronos Workforce Dimensions
Task - Discover which clocks in Fulton County departments are compatible with new system by examining serial numbers and whether the essential departments have these. If not, then which departments can the clocks be taken from. | 2021-02-10 | 2021-02-03 | Started | 100% | bar: Week 2
Presentation- Draft of the presentation that includes the findings and the plan for the upcoming week. | 2021-02-10 | 2021-02-03 | Started | 100% | bar: Week 2
Kronos Clock File - Send the excel spreadsheet that lists where the clocks will be moved to. | 2021-02-12 | 2021-02-10 | Started | 100% | bar: Week 3
Presentation - Make necessary changes and complete the final presentation | 2021-02-12 | 2021-02-12 | Started | 100% | bar: Week 3
Research on both Workforce Systems | 2021-02-14 | 2021-02-18 | Started | 100% | bar: Week 4
Compare and Contrast differences between Workforce Central and Workforce Dimensions | 2021-02-14 | 2021-02-18 | Started | 100% | bar: Week 4
Presentation - Make necessary changes and complete the final presentation showing the advantages of the new system over the old one | 2021-02-18 | 2021-02-19 | Started | 100% | bar: Week 4
Condense list of paycodes | 2021-02-24 | 2021-02-21 | Started | 100% | bar: Week 5
Prepare a presentation detailing Plan A and Plan B | 2021-02-28 | 2021-03-03 | Started | 100% | bar: Week 6
Visit governement center to look at clocks | 2021-03-10 | 2021-03-10 | Started | 100% | bar: Week 7
Create Plan A and Plan B timelines | 2021-03-10 | 2021-03-07 | Started | 100% | bar: Week 7
Review list of Payrules and Pay Codes | 2021-03-17 | 2021-03-14 | Started | 100% | bar: Week 8
Prepare a condensed list of Payrules and Paycodes | 2021-03-21 | 2021-03-17 | Started | 100% | bar: Week 8
Update timelines | 2021-03-24 | 2021-03-25 | Started | 100% | bar: Week 9
Upgrade firmware of 4000 clocks | 2021-03-31 | 2021-03-31 | Started | 100% | bar: Week 10
Visit government to see clock installation | 2021-04-05 | 2021-04-05 | Started | 100% | bar: Week 11
Attend Kronos Training | 2021-04-06 | 2021-04-06 | Started | 100% | bar: Week 11
Work on Final Deliverables | 2021-04-12 | 2021-04-16 | Started | 100% | bar: X Week 12
Capstone Presentation | 2021-04-20 | 2021-04-23 | Started | 100% | bar: X Week 13
| Deadline | Start | Status | Complete? | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Risks/Challenges | Mitigation
Tableau Upgrade Phase 3
Presentation to sponsors based on what we have learned from previous Tableau upgrades from Phases 1 & 2 | 2021-02-09 | 2021-02-01 | Complete | 100% | bar: Week 2 to Week 3
Presentation to convince Sponsors to allow communication with the Email server team | 2021-02-17 | 2021-02-14 | Complete | 100% | bar: Week 4
Presentation to email server team about previous Tableau upgrade documentation to convince them to allow us to run systems tests | 2021-02-21 | 2021-02-17 | Complete | 100% | bar: Week 5
Tableau Blueprint | 2021-03-05 | 2021-02-25 | Complete | 100% | bar: Week 5 to Week 6
Research and create presentation to Sponsors explaining "licensed based management" for the Tableau Server and why we should implement it | 2021-02-25 | 2021-02-21 | Complete | 100% | bar: Week 5
Test and Production Server Rollback of Workbooks & Data Sources | 2021-03-07 | 2021-03-03 | Complete | 100% | bar: Week 6
Finalize the test of the upgrade (Dry-run on test server) | 2021-03-14 | 2021-03-08 | Complete | 100% | bar: Week 7
License Tracking Testing / Implementation with Terrence Slaton | 2021-04-01 | 2021-03-16 | Complete | 100% | bar: Week 8
Server Upgrade Communication Plan | 2021-04-01 | 2021-03-03 | Complete | 100% | bar: Week 9 to Week 10
Perform the Server Upgrade on Production from 10.5 to 2020.2 | 2021-04-12 | 2021-04-10 | Complete | 100% | bar: Week 11
Record "Tableau Fundamentals" eLearning for Final User Manual/ Work with data stewards to republish workbooks | 2021-04-18 | 2021-04-12 | Complete | 100% | bar: Week 12
Final Deliverable 1 -User Manual about Tableau Server / Desktop w/ eLearning Recordings | 2021-04-25 | 2021-04-12 | Complete | 100% | bar: Week 12 to X Week 13
Final Deliverable 2 - Sign off by Project Sponsors on Tableau Blueprint | 2021-04-25 | 2021-04-12 | Complete | 100% | bar: X Week 13
Final Deliverable 3 - Project Infographic | 2021-04-26 | 2021-04-13 | Complete | 100% | bar: X Week 13
Final Presentation | 2021-04-23 | 2021-04-18 | Complete | 100% | bar: X Week 13 to X Week 14
| Deadline | Start | Status | Complete? | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Risk/Challenges | Mitigation
Strategy Office - Data Analytics Project
Week 1: download all necessary software and get logged in to shared drive | 2021-01-29 | 2021-01-26 | Finished | 100% | bar: Week 1
Week 2: create a demo project and upload it to the server | 2021-02-05 | 2021-02-02 | Finished | 100% | bar: Week 2
Week 3: present first dashboard to sponsor | 2021-02-16 | 2021-02-09 | Finished | 100% | bar: Week 3
Week 4: create second dashboard to sponsor | 2021-02-23 | 2021-02-16 | Finished | 100% | bar: Week 4
Week 4: create third dashboard to sponsor | 2021-02-23 | 2021-02-16 | Finished | 100% | bar: Week 4
Week 5: create fourth & fifth dashboard to sponsor | 2021-03-02 | 2021-02-23 | Finished | 100% | bar: Week 5
Week 6: create sixth & seventh dashboard to sponsor | 2021-03-09 | 2021-03-02 | Finished | 100% | bar: Week 6
Week 7: create eighth & ninth dashboard to sponsor | 2021-03-23 | 2021-03-10 | Finished | 100% | bar: Week 7
Week 8: create tenth dashboard to sponsor + optimization | 2021-03-23 | 2021-03-10 | Finished | 100% | bar: Week 8
week 9: optimization of app | 2021-03-30 | 2021-03-23 | Finished | 100% | bar: Week 9
week 10: optimization of app | 2021-04-06 | 2021-03-30 | Finished | 100% | bar: Week 10
Week 11: create 11th & 12th dashboard to sponsor | 2021-04-13 | 2021-04-06 | Finished | 100% | [16 empty] | need to know how to use socrata | learn how to use socrata | bar: Week 11
Week 12: Finishing App | 2021-04-20 | 2021-04-13 | Finished | 100% | bar: Week 12
Week 13: Final Presentation | 2021-04-23 | 2021-04-23 | Not Started | 0% | bar: x Week 13
| Deadline | Start | End | Complete? | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Risk/Challenges | Mitigation
Website Content & Development
Scope & Plan | 2021-02-03 | 2021-01-30 | started | 100% | bar: Week 1
Plan for the website | 2021-02-03 | 2021-01-30 | started | 100% | [16 empty] | Formatting the slides | Use templates of professional powerpoint slide presentations | bar: Week 2
Research: Sitecore, FC Article, Survey | 2021-02-08 | 2021-02-06 | end | 100% | [16 empty] | no access or traning for sitecore | bar: Week 3
Feed back form the client | 2021-04-26 | 2021-02-03 | started | 100% | bar: Week 4
understand Sitecore | 2021-04-26 | 2021-02-05 | started | 100% | bar: Week 5
Whitebord drawing video | 2021-03-20 | 2021-02-05 | end | 100 | [16 empty] | Software to develop whiteboard video | Protoype software idea proposal to Justyna | bar: Week 6
Rule and testing sitecore |  | 2021-02-03 | started | 100% | bar: Week 7
come up with a strategy |  | 2021-02-03 | end | 100% | bar: Week 8
implement a strategy |  | 2021-02-03 | Started | 100% | bar: Week 9
Trials and Tribultation/ testing the strategy |  | 2021-02-03 | Started | 100% | bar: Week 10
Intro Video |  | 2021-03-18 | Started | 100% | [16 empty] | New Video idea to create form zoom videos | bar: Week 11
Video Ideas |  | 2021-03-18 | end | 100% | bar: Week 12
Final changes |  | 2021-04-26 | Started | 90% | bar: x Week 13
Final Prestation |  |  | Not Started | 100% | bar: x Week 14
| Deadline | Start | Status | Complete? | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Risks/Challenges | Mitigation
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%
| Deadline | Start | Status | Complete? | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Risks/Challenges | Mitigation
Networking Team
Research what is "Cisco, ACI, Meraki, Netbrain | 2021-01-27 | 2021-01-20 | complete | 100% | [16 empty] | Completing tasks on personal/necessary equipment | bar: Week 1
Research and understand Fulton County’s current implementation of Cisco ACI infrastructure for Data Centers and Meraki switch and wifi configuration. | 2021-02-03 | 2021-01-28 | complete | 100% | [16 empty] | Accessing networks via personal equipment | Company equipment to be issued | bar: Week 2
Understanding infrastructure and developing a full network diagram utilizing Netbrain automation tool | 2021-02-10 | 2021-02-04 | complete | 100% | [16 empty] | Receiving access and understanding the Netbrain platform | All has been mitigated with the receipt of equipment and Netbrain handbook | bar: Week 3
Report/Presentation- Understand current deployment and provide a report of ACI and Meraki deployment in environment. Network documentation of ACI infrastructure and Network documentation of Meraki | 2021-02-17 | 2021-02-11 | complete | 100% | [16 empty] | The physical network view does not include NSX, CISCO ACI, or ESXi Meraki is not visible in the environment Only one user can use at a time | No mitigation at this time based on the application functionality | bar: Week 4
Evaluate network configuration of Netbrain and remediate gaps | 2021-02-24 | 2021-02-18 | complete | 100% | [16 empty] | Biggest challenge is only one person can use Netbrain at a time | No current work around as it is a functionality of the application | bar: Week 5
Demonstrate use cases for Netbrain within the ACI and Meraki infrastructure. | 2021-03-03 | 2021-02-25 | complete | 100% | [16 empty] | Application license, training, application communication | Additional license, Provide training | bar: Week 6
Live demonstration of monitoring, alerting and troubleshooting utilizing Netbrain | 2021-03-17 | 2021-03-04 | complete | 100% | [16 empty] | Trouble shooting process using Netbrain | Speaking with vendor | bar: Week 7 to Week 8
Guide of how to utilize Netbrain & Meraki including troubleshooting | 2021-03-24 | 2021-03-18 | complete | 100% | bar: Week 8
Training guide for new users |  | 2021-03-29 | complete | 100% | bar: Week 9
|  |  | complete | 100% | bar: Week 10
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%
| Deadline | Start | Status | Complete? | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Risks/Challenges | Mitigation
Cyber Security Capstone Project
Week 1 presentation | 2021-02-04 | 2021-02-01 | Complete | 100% | bar: Week 1
Week 2- best Compiance policies | 2021-02-11 | 2021-02-08 | Complete | 100% | bar: Week 2
Week 3- research how to make policies | 2021-02-18 | 2021-02-17 | Complete | 100% | bar: Week 3
Week 4- Policy application | 2021-03-04 | 2021-02-22 | Complete | 100% | bar: Week 4
Week 5- Guest device policies | 2021-03-18 | 2021-03-15 | Complete | 100% | bar: Week 5
Week 6- Guest device policy making | 2021-03-25 | 2021-03-22 | Complete | 100% | bar: Week 6
Week 7- Continue policy making | 2021-04-01 | 2021-03-29 | Complete | 100% | bar: Week 7
Week 8- Continue policy making | 2021-04-08 | 2021-04-04 | Complete | 100% | bar: Week 8
Week 9- Continue Policy making | 2021-04-15 | 2021-04-12 | Complete | 100% | bar: Week 9
Week 10- Final Presentaiton | 2021-04-23 | 2021-04-19 | Complete | 100% | bar: Week 10
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%
|  |  | Not Started | 0%